## Strategic Planning Checklist
Preserving and Expanding CDFI Minority Depository Institutions
STRATEGIC PLANNING CHECKLIST & TIMELINE |  |  |  |  | Projected Date of Strategic Planning Session
The Strategic Planning Checklist and Timeline can be used as a discussion tool to review the steps in the Strategic Planning process, the roles and responsibilities of the Board of Directors and Management, and as a practical action plan to develop your Strategic Plan. The Strategic Planning Checklist and Timeline is a guide and should be customized to fit the culture, priorities, and objectives of your financial institution. |  |  |  |  | 2014-06-15
Pre-Planning - Activities should occur 4-6 months in advance of Strategic Planning Session
Strategic Planning Preparation | Accountability | Sample Calendar Cycle* | Due By | Status | Details
Convene Board to Discuss Strategic Planning Process | Board & Management | 2014-01-16 |  |  | 1) Develop consensus regarding importance of Strategic Planning 2) Discuss elements of Strategic Planning 3) Identify strategic priorities 4) Select Strategic Planning Committee
Initial Planning Meeting of Strategic Planning Committee | Strategic Planning Committee | 2014-01-23 |  |  | Discuss: 1) Pros and cons of selecting a facilitator versus an internally-led strategic planning session and make recommendations to the Board 2) Discuss the facilitator selection and vendor management process 3) Develop timeline for Strategic Planning process to include budget and date for Strategic Planning session 4) If a facilitator will not be retained, consider who will capture Strategic Planning data during the session and how/when the information will be disseminated 5) Consider the Strategic Plan output that best fits the culture of your institution - such as a summary planning document, a detailed document for the Board and summary document, or a combination of documents.
Strategic Planning Committee Presents Recommended Framework for Strategic Planning to Board of Directors for Approval | Board & Strategic Planning Committee | 2014-02-01 |  |  | Presentation should include: 1) Scope of work for facilitator (if applicable) 2) Proposed Strategic Planning framework: process, session date, budget, and desired outcomes and outputs 3) Draft agenda for Strategic Planning session - elements might include: i) Review of mission/vision/value ii) Review of historical performance/benchmarking iii) Prioritizing results of environmental scan iv) S.M.A.R.T. goal setting v) Summary of next steps and accountabilities
Develop Framework/Template for Environmental Scan, Prioritization Process ,and Benchmarking | Strategic Planning Committee | 2014-03-31 |  |  | 1) Strategic Planning Committee and/or facilitator selects environmental analysis tools that best fit the culture of your institution. Facilitators can be helpful in selecting environmental analysis tools that works for your institution (this could include SWOT or other similar options) 2) Select benchmarking metrics that will best inform the Strategic Planning process 3) Communicate benchmarking metrics to management for execution of data-gathering process
Identify and Prepare Individuals Participating in Strategic Planning Process and Initiate Data-Gathering for Benchmarking | Management | 2014-04-07 |  |  | 1) Identify key staff that will assist in the data-gathering for benchmarking, communicate accountability, and set deadlines for receipt of the data 2) Prepare and distribute a formal communication document to key staff, the Board of Directors, and other participants (i.e. advisory boards, community stakeholders) in the Strategic Planning session that outlines the date for the session, the strategic framework, agenda, environmental scan documents, and deadlines for receipt of any pre-session information
Execute Location/Site Logistics for Strategic Planning Session | Management | 2014-04-14 |  |  | Consider: 1) Retaining a meeting space that is comfortable and free from distractions 2) Access to technology for presentation of data and for use by participants during breaks 3) Flip charts, markers, and other materials required to capture discussion and follow-up items 4) Notepads and other materials for use by participants during the session
Complete Data-Gathering Process for Benchmarking | Management/Key Staff | 2014-04-28 |  |  | It may help to utilize the historical performance review tool and capacity assessment tool. These tools can be customized to fit your institutional priorities and objectives but are great means to start gathering valuable data. Examples of sources of data include reports from your regulatory review, existing excel or system reports, previous/new surveys, internal audit reports, monthly management reports, last year’s strategic plan, your business plan, etc.
Provide S.W.O.T. (or other Environmental Analysis Tools) and Benchmarking Data to Management/Staff/Board | Management | 2014-05-18 |  |  | Select tools that best fit the culture of your institution. Facilitators can also be helpful in selecting environmental analysis tools. Prioritization of environmental scan elements can be done prior to our during the Strategic Planning session. In either scenario, priorities should be tested against the mission, vision, values, and objectives of your institution.
Post-Strategic Planning Session - Activities should occur within 60 days after the Strategic Planning Session
Strategic Plan Development & Implementation | Accountability | Sample Calendar Cycle* | Due By | Status | Details
Provide First Draft of Strategic Plan and Goals | Strategic Planning Committee/Designee or Facilitator | 2014-07-15 |  |  | Make any required edits to the Strategic Plan and Corollary Action Plans. Coordinate with Management for the procurement of any follow-up data required for inclusion in the Strategic Plan or any supplemental data requested during the Strategic Planning Session
Review and Edit Strategic Plan and Goals | Strategic Planning Committee/Designee and/or Facilitator | 2014-07-30 |  |  | Management should also weigh-in on edits to the Strategic Plan and Corollary Action Plans
Board Review & Adoption of Strategic Plan | Board | 2014-08-06 |  |  | Should include a final review of Strategic Plan by the Board
Final Edits to Strategic Plan | Strategic Planning Committee/Designee and/or Facilitator | 2014-08-13 |  |  | Incorporate any final updates requested by the Board
Internal Communication on Strategic Plan | Management | 2014-08-27 |  |  | The internal communication of the Strategic Plan* should: 1) reinforce the mission, vision, and values of the Bank 2) provide a summary of your Strategic Plan 3) relate the Strategic Plan objectives to the day-to-day activities of employees to promote accountability 4) Provide action plan templates (related to Strategic Plan objectives) to staff and tie-in to budget planning based on resource requirements *Provide annual (or more frequent updates) on progress towards meeting Strategic Planning objectives to keep staff engaged, energized and accountable
Establish Action Plan for Each S.M.A.R.T.. Goal | Management & Key Staff | 2014-09-10 |  |  | As applicable, management should require key staff to identify departmental goals and timelines to achieve the S.M.A.R.T. Goals
Review Action Plans & Progress | Management & Key Staff | ongoing |  |  | Review and update progress towards goals and Strategic Plan objectives on a quarterly basis, at minimum.
Review Strategic Plan Progress | Board & Management | ongoing |  |  | Strategic Plans should be reviewed on a regular basis and updated as required based on changes in priorities. Management should provide updates on action plans that affect the achievement of Strategic Planning goals.